## IT Projects Risk Assessment Sco
IT Application Development Project Risk Assessment Scorecard for
_________ Application
1. Sourcing Risks |  | Y | N | 3. Requirements Risks |  | Y | N
a. | Has a single vendor been selected as a prime contractor for the development of the application? |  |  | a. | Has the new business process that the application is automating been fully designed and documented?
b. | Has the prime vendor agreed to and provided a firm-fixed price bid? |  |  | b. | Is the new business process fully supported by all stakeholders?
c. | Does the prime vendor have experience working with this Customer? |  |  | c. | Has the business fully defined their requirements?
d. | Do all vendors have significant application development experience? |  |  | d. | Have the business requirements been translated into system requirements by the IT team?
e. | Does the prime vendor have a well-defined and institutionalized development process? |  |  | e. | Have the system requirements been validated with prototypes?
f. | Do all vendors have the resources to handle the size of this project? |  |  | f. | Is their a well-defined and institutionalized change control process for requirements?
g. | Do all vendors have significant experience with all the tools selected? |  |  |  |  | 0 | 0
|  |  |  | 4. Technical Risks |  | Y | N
h | Are all vendors financially stable?
|  |  |  | a. | Is the project not planning to use a technology new to the industry?
|  | 0 | 0
2. Project Organization Risks |  | Y | N | b. | Is project not planning to use a technology new to the Customer?
a. | Is there a well-defined organizational structure for the project? |  |  | c. | Is the project not dependent upon a future release of a vendor’s product?
b. | Has the business assigned a Customer employee as a full-time program manager |  |  | d. | Has a thorough infrastructure assessment been performed?
c. | Has a Customer employee been assigned to this project as a full-time IT project manager? |  |  | e. | Has the hosting environment been well defined?
d. | Does the assigned business program leader have experience leading projects of this type? |  |  | f. | Is there a test environment that appropriately mirrors the production environment?
e. | Does the assigned IT project leader have experience leading projects of this type? |  |  |  |  | 0 | 0
f. | Have the needs for subject matter experts been quantified for the entire project? |  |  | 5. Planning Risks |  | Y | N
g. | Has a program management office been established? |  |  | a. | Does the plan include the appropriate time and cost contingency?
h. | Is the IT organization responsible for this project experienced in developing large applications? |  |  | b. | Does the plan include the appropriate time and cost to perform all data conversions?
i. | Is there a high sense of teamwork between the business and IT teams? |  |  | c. | Does the plan include the appropriate time and cost to develop all interfaces?
j. | Is there a clear senior executive in the business who is championing this project? |  |  | d. | Does the plan include the appropriate time and cost to perform all appropriate testing
k. | Have all stakeholders been engaged in the projects? |  |  | e. | Does the plan include the appropriate time and cost to prepare and conduct both process and system training
|  | 0 | 0 | f. | Is the project not dependent upon any other separate projects?
|  |  |  | g. | Does the plan identify other initiatives that need to be coordinated with during deployment?
|  |  |  | h. | Is there a plan to conduct a thorough pre-deployment readiness review with all stakeholders?
[6 empty] | 0 | 0
[9 empty] | Yes | No
[8 empty] | Total | 0 | 0
[8 empty] | Planning | 0 | 0
[8 empty] | Technical | 0 | 0
[8 empty] | Requirements | 0 | 0
[8 empty] | Organization | 0 | 0
[8 empty] | Sourcing | 0 | 0

## Instructions
IT Application Development Project Risk Assessment Scorecard
The purpose of the IT Application Development Project Risk Assessment Scorecard is to proactively identify risks of major IT projects. Using a common Risk Assessment Scorecard that identifies risks will allow us to take appropriate steps avoid these risks where possible and if not then to mitigate risks when they happen.
The Risk Assessment Scorecard consists of known categories of project risk. The IT Application Development Project Risk Assessment Scorecard must be completed for all projects over $2.5 million. The Risk Assessment Scorecard is to be included as an element of the AR package that is reviewed with Dan McNicholl for project approval. The AR request typically takes place at the end of the Define stage of the SDP-21 process.
The IT Application Development Project Risk Assessment Scorecard provides a total project risk score. This score will help us to better understand the inherent risks of a project. There is no passing or failing grade! Each project will be evaluated in its own context (other key IT projects, risk/return profile, etc.).
Fill in your project name at the top and then just place an 'X' in the appropriate checkbox, Yes or No, for each question. Be sure to answer all questions giving one answer to each. The graph will automatically be updated for your responses.
The Lead Project or Program Manager is responsible for completing the risk assessment. If you have any questions please contact Rudy Vriendts at 0031 620 35 67 51 8 or via email: Rudy.Vriendts@Allturn-Projecten-Nederland.com <Press Enter for automatic email sending>